## Overview
Timeline - Master Thesis
Topic: Model Predictive Control Based Trajectory Generation for Low Speed Scenarios, Authour : Krishna Satish D S
|  | October |  |  |  | November |  |  |  | December |  |  |  | January |  |  |  | February |  |  |  | March |  |  |  | April
|  | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2
Literature survey | Different Techniques to solve the problem in hand | October W1: Laptop Setup; October W2: Literature survey
MPC and it’s variations | bar: October W1 to October W3
Decision on the concept (Details) | Detailed Analysis of MPC and OCP shooting methods , motion models and so on | October W3: Decision on the concept
CasADI overview | bar: October W3 to October W4
Preparing the frame work | Getting acquainted with CasADI and ROS2 | October W4: Preparing the frame work
Implementing and testing simple example packages from CasADi website, | bar: October W4 to November W2
Implementation | Matlab implementation | November W2: implementation
Testing | bar: November W2 to January W2
Trying new constraints | bar: November W2 to January W2
Different Shooting methods | bar: November W2 to January W2
Python implementation | bar: November W2 to January W2
OOPS implementation | bar: November W2 to January W2
Carla Integration | bar: November W2 to January W2
Testing/ validating the model | Testing | January W1: Testing/ validating the model
Documentation | Writing | November W1: Table Of Content; December W1: Documentation; December W3: Documentation; January W1: Documentation; January W4: Documentation; February W2: Documentation; February W4: Documentation; March W2: Initial Review; April W1: Buffer Time and Demos